## EXTRAIT FONCTIONS
Type of the Diagram | Reference | Name of the Function | DFD | FUNCTION | Agreed function | Complexity | Group | PIC | Deadline | Status | Already analysed
DFD | Context­Diagram | Board_External_Interface | 1
DFD | 0 | GATC TRAINBORNE SUB SYSTEM | 1
DFD | 1 | Filter_information_from_ERTMS_trackside (including linking) | 1 | 1 | 1 | 3 |  | Group 1 | 2013-11-15 |  | some inputs available
DFD | 2 | Provide_automatic_train_protection | 1
DFD | 2.1 | Manage_STMs | 1 | 1 | 1 | 3
PS | 2.2 | Determine_train_location_information |  | 1 | 1 | 3 |  | Group 4 | 2013-11-15 |  | some inputs available
PS | 2.3 | Control_route_suitability |  | 1 | 1 | 1 | group 2 | Group 1 | 2013-11-15 | Draft
PS | 2.4 | Manage_track_conditions |  | 1 | 1 | 2 |  | Group 2 | 2013-11-15
DFD | 2.5 | Ensure_train_protection | 1
PS | 2.5.1 | Manage_reception_of_MA_information |  | 1 | 1 | 2 |  | Group 3 | 2013-11-15 |  | some inputs available
PS | 2.5.2 | Manage_TSR |  | 1 | 1 | 1 | group 4 | Group 2 | 2013-11-15 | Draft | some inputs available
DFD | 2.5.3 | Manage_Speed_Supervision_Inputs | 1 | 1 | 1 | 2 |  |  |  |  | some inputs available
|  | Activate_train_protection_in_FS | 1 | 1 | 1 | 3
|  | Activate_train_protection_in_OS |  |  | 1 | 3
|  | Activate_train_protection_in_LS |  |  | 1 | 3
|  | Activate_train_protection_in_SR | 1 | 1 | 1 | 2
|  | Activate_train_protection_in_UN | 1 | 1 | 1 | 2
|  | Activate_train_protection_in_SH |  | 1 | 1 | 2
|  | Activate_train_protection_in_TR |  | 1 | 1 | 2
|  | Activate_train_protection_in_SF |  | 1 | 1 | 1
|  | Activate_train_protection_in_SB |  | 1 | 1 | 2
|  | Activate_train_protection_in_PT |  | 1 | 1 | 2
|  | Activate_train_protection_in_RV |  | 1 | 1 | 2
|  | Activate_train_protection_in_IS |  | 1 | 1 | 1
|  | Perform train protection |  | 1 | 1 | 3
|  | Perform train protection related actions |  | 1 | 1 | 3
|  | Activate_train_protection_in_SN |  | 1 | 1 | 2
|  | Activate_train_protection_in_PS | 1 |  | 1 | 2
|  | Activate_train_protection_in_NP |  | 1 | 1 | 1
PS | 2.5.14 | Manage_emergency_stop_messages |  | 1 | 1 | 2
|  | Manage_MA_request_for_entry_into_level_2 | 1
DFD | 2.6.3 | Manage_mode_and_level_and_procedures_and_ancillary_functions |  | 1 | 1 | 3
PS | 2.6.1 | compute_mode |  | 1 | 1 | 2
PS | 2.6.2 | compute_level |  | 1 | 1 | 2
DFD | 2.6.3 | Manage_procedures |  | 1 | 1 | 2
PS | 2.6.3.1 | capture_data_for_mission |  | 1 | 1 | 2
PS | 2.6.3.2 | handle_mode_profile_procedure |  | 1 | 1
PS | 2.6.3.3 | handle_SH_procedure | 1 |  | 1
PS | 2.6.3.4 | handle_RV_procedure |  | 1 | 1
PS | 2.6.3.5 | handle_override_EOA |  | 1 | 1
|  | change_of_driver_procedure |  | 1
DFD | 2.6.4 | Perform_ancillary_functions |  | 1
PS | 2.6.4.1 | Manage_track_ahead_free |  | 1 | 1 | 2
PS | 2.6.4.2 | Display_text_messages_coming_from_trackside |  | 1 | 1 | 1 | group1
PS | 2.6.4.3 | Display_geographical_position |  | 1 | 1 | 1 | all | Group 3 | 2013-11-15 | Draft | some inputs available
PS | 2.6.4.4 | End_mission |  | 1 | 1 | 1 |  | Group 4 | 2013-11-15
PS | 2.6.4.5 | Manage_national_values |  | 1 | 1 | 1 | group3 | Group 4 | 2013-11-15 | Draft
PS | 2.6.4.6 | store_configuration_data |  | 1 | 1 | 1 |  | Group 1 | 2013-11-15
|  | Management of MA request |  |  | 1 | 2
|  | Sending of position report |  |  | 1 | 1 |  | Group 2 | 2013-11-15 |  | some inputs available
|  | Determine train integrity |  |  | 1 | 1 |  | Group 3 | 2013-11-15
|  | Declare_master_onboard |  | 1
PS | 2.6.4.8 | Detect_change_of_orientation |  | 1 | 1 | 2
|  | Monitor_tilting_state | 1 | 1
|  | centralise_brakes_commands | 1 | 1
DFD | 6 | Manage_cold_movement_detection | 1 | 1 | 1 | 1
PS | 3 | Provide_train_movement information |  | 1 | 1
DFD | 4 | Manage_radio_sessions | 1 | 1 | 1
DFD | 5 | Record_juridical_data | 1 |  | 1 | 2
DFD | 6 | Interface with train |  |  | 1 | 2
PS | 8 | Interface with DMI |  |  | 1 | 2
Perform_tests
Interface with KMC
|  |  |  | 46 | 51

## Groups
| Group 1 | Group 2 | Group 3 | Group 4 | Data Dictionary
Stephane Besure | X
Nicolas Boverie |  | X |  |  | X
Christian Giraud |  | X
Baseliyos Jacob | X
Vincent Nuhaan |  |  | X
Jan Welvaarts |  |  | X |  | X
Uwe Steinke |  |  |  | X
Marielle Petit-Doche | (X) | (X) | (X) | (X)
Guillaume Durand |  | X
Jan Welte |  |  |  | X
Bernd Hekele |  |  | X |  | X
Yoann Guyot | X
Niklas Schaffrath |  |  |  | X
leader